## Assumptions
Note:
1 | Resource grade wise costing to be defined
2 | Infrastructure costs are not factored in this
3 | Customisation effort/costs are not factored in this
Client Size Definition: Categorized based on the avergage booking volume per month of 'n'
| Client Size Defintion | Booking Volume Per Month | Pre-Live Effort in Hours | Go-Live Effort in Hours | Post-Live Effort in Hours | Total in Hours | Total in PD
| Public Cloud | 100 - 1000 | 491.25 | 40 |  | 531.25
| Private Cloud | 1001 - 3000 | 1064.5 | 64 |  | 1128.5
| Private Cloud Large | >3001 | 1596.5 | 112 |  | 1708.5
Team Size : 75

## Summary
| Public Cloud | Private Cloud ( Hybrid) | Private Cloud [LARGE]
| Cost | Cost | Cost
Setup cost- One time | 6567 | 14118 | 21654
Running Cost -Services/ month | 570.24 | 3801.6 | 12672
Hosting Cost | 1000 | 8500 | 15000
Hosting Additional Servers | NA |  | 5000
Enterprise DbServer | NA |  | 5000
SSL, domain, other certificate, software direct cost | 16.6667 | 41.6667 | 41.6667
Total Running Cost/ Month without addl servers and std licenses | 1586.9067 | 12343.2667 | 37713.6667
Product Cost/month | 1500 | 6000 | 25000

## Costing Details
Rezopia Implementation Effort & Costing Summary
|  |  | Public Cloud |  |  | Private Cloud |  |  | Private Cloud [LARGE]
| Phase | Project Stage | Total Effort in Person Hours | Per Hour Cost in US$ | Total Costing in US$ | Total Effort in Person Hours | Per Hour Cost in US$ | Total Costing in US$ | Total Effort in Person Hours | Per Hour Cost in US$ | Total Costing in US$
| Phase 1 | Project Initiation Phase | 65 | 12 | 780 | 114 | 12 | 1368 | 138 | 12 | 1656
| Phase 2 | Analysis & Environment Creation | 148 | 12 | 1776 | 206 | 12 | 2472 | 328 | 12 | 3936
| Phase 3 | Implementation | 128.25 | 12 | 1539 | 432.5 | 12 | 5190 | 640.5 | 12 | 7686
| Phase 4 | Training | 30 | 12 | 360 | 40 | 12 | 480 | 80 | 12 | 960
| Phase 5 | Pre-Live & UAT Testing | 120 | 12 | 1440 | 272 | 12 | 3264 | 410 | 12 | 4920
| Phase 6 | Go-Live | 56 | 12 | 672 | 112 | 12 | 1344 | 208 | 12 | 2496
|  | TOTAL Setp Cost | 547.25 |  | 6567 | 1176.5 |  | 14118 | 1804.5 |  | 21654
|  |  | Daily |  | 22
| Phase 7 | Post-Live Support [Sustenance] | 18 | 12 | 4752 | 12 | 12 | 3168 | 40 | 12 | 10560
|  | Over head |  |  | 950.4 |  |  | 633.6 |  |  | 2112
|  | Monthly Recurring |  |  | 5702.4 |  |  | 3801.6 |  |  | 12672
570.24
| AWS | Production | 1 |  | 1000 | 1 |  | 8500 | 1 |  | 15000
| AWS | STG/ TRG |  |  |  | 1 |  | 3000 | 1 |  | 5000
| AWS | Software Lic Cost | [5 empty] | 5000 |  |  | 5000
| Other | SSL, domain, other direct cost |  |  | 16.6667 |  |  | 41.6667 |  |  | 41.6667
|  | Product Cost | 1500 | 6000 | 15000
| Licence / Product Cost |  | 10 | 10 | 5
|  |  | 15000 | 60000 | 75000 |  | 150000
Note on E3: Rezopia: Per Hour Cost for Sonata
Note on H3: Rezopia: Per Hour Cost for Sonata
Note on K3: Rezopia: Per Hour Cost for Sonata

## Impl-Effort-Detail
Rezopia Implementation Effort |  |  |  | Public Cloud |  |  |  |  | Private Cloud |  |  |  |  | Private Cloud [LARGE]
# | Phases | Project Stages | Task Breakdown Brief | Effort in Hours | Res. Count | Total Hours | Effort in P.Days | Notes | Effort in Hours | Res. Count | Total Hours | Effort in P.Days | Notes | Effort in Hours | Res. Count | Total Hours | Effort in P.Days | Notes | Sonata Team | Responsibility | Deliverable | Remarks
1 | Phase 1 | Project Initiation Phase
1.1 |  | (5 - 15 Person days) | Requirement Workshop/Meeting | 20 | 2 | 40 | 5 | Conducted from Sonata Offshore via Telecon/GotoMeeting | 32 | 2 | 64 | 8 | Conducted from Client's office @ Onsite | 40 | 2 | 80 | 10 | Conducted from Client's office @ Onsite | 1 PM & 1 BA | Joint: Sonata & Client |  | Rezopia and Client team members are brought together to review detail project requirements, go over Rezopia product in detail and agree on the project deliverables, roles and communication plan
1.2 |  |  | Rezopia Project Checklist | 1 | 1 | 1 | 0.125 |  | 1 | 2 | 2 | 0.25 | Documentation complete & submit from offshore | 1 | 2 | 2 | 0.25 | Documentation complete & submit from offshore | 1 PM & 1 BA | Joint: Sonata & Client | Project Checklist | Project Checklist will be prepared & agreed with the client
1.3 |  |  | Gap Analysis & Requirement Mapping | 8 | 2 | 16 | 2 |  | 16 | 2 | 32 | 4 |  | 16 | 2 | 32 | 4 |  | 1 PM & 1 BA | Joint: Sonata & Client | Gap Analysis & Requirement document | Conduct gap analysis between Client Requirements and Rezopia product and identify customizations and priorities
1.4 |  |  | Project Plan | 4 | 2 | 8 | 1 |  | 8 | 2 | 16 | 2 |  | 12 | 2 | 24 | 3 |  | 1 PM & 1 BA | Sonata | Project Plan | Create a project plan to include key milestones and checkpoints
|  | Sub-Total |  | 33 | 1.75 | 65 | 8.125 |  | 57 | 2 | 114 | 14.25 |  | 69 | 2 | 138 | 17.25
2 | Phase 2 | Analysis & Environment Creation
2.1 |  | (15 - 20 Person days) | Initial Server Setup | 12 | 2 | 24 | 3 | Conducted from Sonata Offshore | 14 | 2 | 28 | 3.5 | Conducted from Sonata Offshore | 16 | 2 | 32 | 4 | Conducted from Sonata Offshore | PM-Infra (0.25), Consultant(1), PM (0.25) QA(0.5) | Sonata | Base Rezopia Product Install Ready
2.2 |  |  | Rezopia Software Installation & Access provision | 48 | 2 | 96 | 12 | Conducted from Sonata Offshore | 54 | 2 | 108 | 13.5 | Conducted from Sonata Offshore | 64 | 2 | 128 | 16 | Conducted from Sonata Offshore | PM-Infra (0.25), Consultant(1), PM (0.25) QA(0.5) | Sonata | Client team to get access to the server
2.3 |  | (3 - 10 Person days) | Fixes / Configurations/settings etc | 16 | 1.75 | 28 | 3.5 | Conducted from Sonata Offshore | 40 | 1.75 | 70 | 8.75 | Conducted from Sonata Offshore | 96 | 1.75 | 168 | 21 | Conducted from Sonata Offshore | PM (0.25) BA (1) TS (0.50) | Sonata | 1) Update Master Project Plan 2) Approach & FSD for enhancements | The cost for these enhancements will be separate including FSD creation
|  | (10 - 20 Person days) | Create Approach/FSD document for enhancements* | NA | NA | NA | NA | Will get upgrade as part of Roadmap
|  | Sub-Total |  | 76 | 1.9167 | 148 | 18.5 |  | 108 | 1.9167 | 206 | 25.75 |  | 176 | 1.9167 | 328 | 41
3 | Phase 3 | Implementation
3.1 |  | (2 - 5 Person days) | Rezopia System Configuration | 16 | 1 | 16 | 2 | Conducted from Sonata Offshore | 32 | 1 | 32 | 4 | Conducted from Sonata Offshore | 40 | 1 | 40 | 5 | Conducted from Sonata Offshore | QA (0.5) BA (0.5) | Sonata
3.2 |  | (10 - 25 Person days) | Products data loading | 40 | 1 | 40 | 5 | Conducted by Client from his office | 80 | 2 | 160 | 20 | Conducted by Client from his office | 100 | 2 | 200 | 25 | Conducted by Client from his office | Consultants (2-3) | Client | Product data ready
3.3 |  | (15 - 45 Person days) | 3rd Party Interface Certification | 8 | 5 | 40 | 5 | 2 partner products | 40 | 5 | 200 | 25 | Conducted from Sonata Offshore | 72 | 5 | 360 | 45 | Conducted from Sonata Offshore | Dev (2) QA(1) BA(1) PM(0.25) TS (0.75) | Sonata
3.4 |  | (5 Person days) | System testing by QA team | 21.5 | 1.5 | 32.25 | 4.0312 | Conducted from Sonata Offshore | 27 | 1.5 | 40.5 | 5.0625 | Conducted from Sonata Offshore | 27 | 1.5 | 40.5 | 5.0625 | Conducted from Sonata Offshore | Dev (0.25) QA(1) Infra(0.25) | Sonata | 1) Application Testing Complete 2) Update Master Project Plan
|  | Sub-Total |  | 85.5 | 2.125 | 128.25 | 16.0312 |  | 179 | 2.375 | 432.5 | 54.0625 |  | 239 | 2.375 | 640.5 | 80.0625
4 | Phase 4 | Training
4.1 |  | (5 - 10 Person days) | Application training to key users | 30 | 1 | 30 | 3.75 | Web based training from Sonata Office @ Offshore | 40 | 1 | 40 | 5 | In-Person training @ Clients Office [Onsite] | 80 | 1 | 80 | 10 | In-Person training @ Clients Office [Onsite] | BA(1) | Sonata | 1) Web based / In-person training on Rezopia product 2) Walkthrough on Online Product Help
|  | Sub-Total |  | 30 | 1 | 30 | 3.75 |  | 40 | 1 | 40 | 5 |  | 80 | 1 | 80 | 10
5 | Phase 5 | Pre-Live & UAT Testing
5.1 |  | (5 - 10 Person days) | Final Pre-Live Testing by QA team | 40 | 1 | 40 | 5 | Coordinated with client from Sonata Office @ Offshore | 40 | 2 | 80 | 10 | Coordinated with client from Sonata Office @ Offshore | 80 | 1 | 80 | 10 | Conducted in coordination with the Client [Onsite] | QA(0.5) BA(0.5) | Sonata | 1) Final Pre-Live Application Testing Complete 2) Update Master Project Plan
5.2 |  | (30 - 40 Person days) | User Acceptance Testing | 40 | 2 | 80 | 10 | Coordinated with client from Sonata Office @ Offshore | 96 | 2 | 192 | 24 | Coordinated with client from Sonata Office @ Offshore | 110 | 3 | 330 | 41.25 | Coordinated with the client [Onsite] | BA(1) PM(1) UAT(2-5) | Client | Product Testing Complete | Client team will perform a standard user testing to make sure that they are ready to go live
|  | Sub-Total |  | 80 | 1.5 | 120 | 15 |  | 136 | 2 | 272 | 34 |  | 190 | 2 | 410 | 51.25
6 | Phase 6 | Go-Live | +/- 3 days effort for 24X7 required | 8 | 2 | 16 | 2 |  | 24 | 2 | 48 | 6 |  | 48 | 2 | 96 | 12 |  | 24x7 team | Sonata/Client | stand by
|  | (5 - 10 Person days) | Monitor Production Environment | 8 | 2 | 16 | 2 | Coordinated with client from Sonata Office @ Offshore | 8 | 5 | 40 | 5 | Coordinated with client from Sonata Office @ Offshore | 16 | 5.5 | 88 | 11 | Conducted in coordination with the Client [Onsite] | Infra (1) TS (0.5) Dev (2) PM (1) QA (1) | Sonata |  | The task ranges from the actual installation and configuration of the production servers for live traffic.
|  | (2 - 3 Person days) | Rollout | 8 | 3 | 24 | 3 | Coordinated with client from Sonata Office @ Offshore | 8 | 3 | 24 | 3 | Coordinated with client from Sonata Office @ Offshore | 8 | 3 | 24 | 3 | Conducted in coordination with the Client [Onsite] | PM(1) UAT(2) | Client | 1) Provide Testing support to client 2) Rezopia Support process kick-off | Typical rollouts will first go live for a small number of users and then rollout over a period of time to all the users
|  | Sub-Total |  | 24 | 7 | 56 | 7 |  | 40 | 10 | 112 | 14 |  | 72 | 10.5 | 208 | 26
7 | OnGoing | Post Go-Live Support | Per Day Avg for set of 10 customer
|  |  | CS Support | 8 | 1 | 8 | 1 |  | 4 | 1 | 4 | 0.5 |  | 8 | 1 | 8 | 1
|  |  | Infra Support | 4 | 1 | 4 | 0.5 |  | 2 | 1 | 2 | 0.25 |  | 8 | 1 | 8 | 1
|  |  | Engineering | 4 | 1 | 4 | 0.5 |  | 4 | 1 | 4 | 0.5 |  | 8 | 2 | 16 | 2
|  |  | QA | 2 | 1 | 2 | 0.25 |  | 2 | 1 | 2 | 0.25 |  | 8 | 1 | 8 | 1
|  | Sub-Total |  | 18 | 4 | 18 | 2.25 |  | 12 | 4 | 12 | 1.5 |  | 32 | 5 | 40 | 5

## 1.Initiation
Initiation Steps
S.No | Tasks | Responsibility | Effort hours for Public Cloud client | Effort hours for Private Cloud client | Effort hours for Private Cloud client [LARGE] | Remarks
1 | Project Proposal Kick off meeting | Rezopia Business
2 | Understanding client requirements through RFP | Rezopia Business
3 | Project Checklist preparation | Rezopia Business
4 | Kick off meeting at client place or clients visits ( On Request ) | Rezopia Business
5 | Gap analysis from RFP | Rezopia Business
6 | Prepare high level estimates based on Gap analysis | Rezopia Eng
7 | Prepare MSA and get it signed off | Rezopia Business
8 | Preparation of Project plan for customer | Rezopia Eng
9 | Review meeting with customer on project plan and finalize it | Rezopia Eng
| Total |  | 0 | 0 | 0
Note: Based on the client size, these efforts might need to be updated/looked-at

## 2. Initial Server_Setup
Initial Server Setup Tasks
S.No | Tasks | Responsibility | Effort hours for Public Cloud client | Effort hours for Private Cloud client | Effort hours for Private Cloud client [LARGE] | Remarks
1 | New tenant creation in Local Environment | Rezopia Infra | 2
2 | Take the backup of the tenant database and the metadata insert scripts | Rezopia Infra | 1
3 | Move the backup to the SAAS Cloud environment | Rezopia Infra | 1
4 | Execute the metadata insert script | Rezopia Infra | 4
5 | Metadata tenant table settings | Rezopia Infra
6 | Restore the tenant in the SQL instance | Rezopia Infra
7 | Tenant Appsetting table settings | Rezopia Infra
8 | Tenant sites table settings | Rezopia Infra
9 | Tenant tenantsite table settings | Rezopia Infra
10 | Create the tenant folders in the media | Rezopia Infra
11 | Create the DNS names for the B2B and B2C sites | Rezopia Infra | 3
12 | Create the DNS names for microsites if any | Rezopia Infra
13 | Generate the CSR file for the newly added sites and get the SSL installed | Rezopia Infra
14 | Solr configuration for the new tenant added | Rezopia Infra | 2
15 | Restart the services | Rezopia Infra | 1
16 | Reset the IIS | Rezopia Infra
17 | Run the required batchprocess | Rezopia Infra
18 | Sanity check | Rezopia Infra | 2
| Total |  | 16 | 0 | 0
Note: Based on the client size, these efforts might need to be updated/looked-at

## 3.Implementation
Implementation Steps
S.No | Tasks | Responsibility | Effort hours for Public Cloud client | Effort hours for Private Cloud client | Effort hours for Private Cloud client [LARGE] | Remarks
1 | Test Case suite will be executed based on client setup | Rezopia QA | 16 | 24 | 48
2 | UI Header & Footer changes based on client request | Rezopia UI | 16 | 24 | 40
3 | Post Data loading support - Data corrections, validation, review etc.. | Rezopia QA | 24 | 24 | 48
4 | Building Location data index for autocomplete | Rezopia Eng | 8 | 8 | 8
5 | Partner content caching (If partner is included) | Rezopia Eng | 8 | 8 | 8
6 | Verifying the functions of MSMQ | Rezopia Eng | 8 | 8 | 8
7 | Encryption of payment gateway signatures in DB | Rezopia Eng | 8 | 8 | 8
8 | Update SeedData ( Category widget, Notification templates and vouchers) | Rezopia Eng | 8 | 12 | 16
9 | Update appsetting (Multi language , DateFormat etc) as per client request | Rezopia Eng | 8 | 12 | 16
10 | Resolving issues if any due to environment or data | Rezopia Eng | 16 | 24 | 36
11 | Other Enhancement/Task | Rezopia Eng | 16 | 24 | 36
12 | Certification for go live/UAT | Rezopia QA | 16 | 24 | 36
| Total |  | 152 | 200 | 308
Note: Based on the client size, these efforts might need to be updated/looked-at

## 4.Training
Training
S.No | Tasks | Responsibility | Effort hours for Public Cloud client | Effort hours for Private Cloud client | Effort hours for Private Cloud client [LARGE]
1 | Rezopia product overview | Client Service Team | 2 | 2 | 4
2 | Training of consumer site | Client Service Team | 1 | 1 | 2
3 | Training of Agency site | Client Service Team | 1 | 1 | 2
4 | Training of Call Center | Client Service Team | 1 | 2 | 4
5 | Configutaion of Supplier setup | Client Service Team | 4 | 6 | 12
6 | Configuration of Product setup | Client Service Team
7 | Configuration of Add-on setup | Client Service Team
8 | Inventory setup | Client Service Team | 8 | 10 | 20
9 | Pricing setup | Client Service Team
10 | Surcharge setup | Client Service Team
11 | Markup setup | Client Service Team
12 | comission setup | Client Service Team
13 | Tax setup | Client Service Team
14 | Multi currency setup | Client Service Team
15 | Fare Basis & Fare Rules | Client Service Team | 4 | 6 | 12
16 | Contract Conditions | Client Service Team
17 | Policies | Client Service Team
18 | Coupons | Client Service Team
19 | Package setup | Client Service Team | 9 | 12 | 24
20 | Package option override price setup | Client Service Team
| Total |  | 30 | 40 | 80

## 5. Pre-Golive
Pre-GoLive Tasks |  | Legend: Mandatory to be checked by Client team before Go Live
S.No | Section | Component / Tasks | Responsibility | Effort hours for Public Cloud client | Effort hours for Private Cloud client | Effort hours for Private Cloud client [LARGE] | Remarks
1 | Consumer Site | Provide Site Header and Footer preferences | <Client>
|  | Define Terms & Conditions | <Client>
|  | "Checkout as guest" to be turned ON - Preference | <Client>
|  | Setup the Profile Attributes, Booking Attributes | <Client>
|  | Provide Notifications / Vouchers / Invoices Header and Footer preferences | <Client>
|  | Provide Support Email | <Client>
|  | SSL - Should have admin@domainname.com | <Client>
|  | Provide Meta Tags, Site Description & Page title | <Client>
|  | Verify whether site Header and Footer are configured | Rezopia QA & BA
|  | Verify whether Terms & Conditions are defined | Rezopia QA & BA
|  | Verify if "Checkout as guest" is turned ON or OFF (according to tenant's preference) | Rezopia QA & BA
|  | Verify the Profile Attributes, Booking Attributes (according to tenant's preference) | Rezopia QA & BA
|  | Verify whether Notification Header and Footer is defined | Rezopia QA & BA
|  | Verify whether Support Email is entered | Rezopia QA & BA
|  | Verify whether SSL certificate is installed and COMODO logo is appearing in Checkout page | Rezopia QA & BA
2 | Agency Site | Provide Site Header and Footer preferences | <Client>
|  | Define Terms & Conditions | <Client>
|  | "Checkout as guest" to be turned ON - Preference | <Client>
|  | Setup the Profile Attributes, Booking Attributes | <Client>
|  | Provide Notifications / Vouchers / Invoices Header and Footer preferences | <Client>
|  | Provide Support Email | <Client>
|  | Verify whether site Header and Footer are configured | Rezopia QA & BA
|  | Verify whether Terms & Conditions are defined | Rezopia QA & BA
|  | Verify if "Checkout as guest" is turned ON or OFF (according to tenant's preference) | Rezopia QA & BA
|  | Verify the Profile Attributes, Booking Attributes (according to tenant's preference) | Rezopia QA & BA
|  | Verify whether Notification Header and Footer is defined | Rezopia QA & BA
|  | Verify whether Support Email is entered | Rezopia QA & BA
|  | Verify whether SSL certificate is installed and COMODO logo is appearing in Checkout page | Rezopia QA & BA
3 | Branches | Create Branches | <Client>
4 | User Creation | Create User | <Client>
|  | Assign Access rights | <Client>
|  | Assign Branch | <Client>
|  | Assign Supervisor | <Client>
5 | Supplier | Supplier Contact Details | <Client>
|  | Supplier Billing relationship and commissions | <Client>
6 | SMTP Settings | Verify if tenant is using their own SMTP server (if yes, then Server name, username, password should be present) or Rezopia's SMTP server | Rezopia QA & BA
7 | Notification | Notifications needs to be verified for correct keywords, to & from email ids and message content. | <Client>
|  | Verify the approved Notifications content and configurations | Rezopia QA & BA
|  | Verify whether the "From", "To", "CC", "BCC" address is according to tenant's preference (eg: @clientdomain.com not as admin@rezopia.com) | Rezopia QA & BA
|  | Notification History, Notification Queue - Remove all the notifications | Rezopia QA & BA
8 | Markup | Markups needs to be reverified for all the products/packages | <Client>
9 | Tax Templates | Verify the correctness of templates (if tenant preferred GST Tax Invoice) | Rezopia QA & BA
10 | Voucher Templates | Verify all the Voucher templates | <Client>
11 | Codes & Numbers | Series of Booking / Quote numbers preference - To be provided to Rezopia team | <Client>
12 | Consumer Code | Auto Generated / Manual | Rezopia QA & BA
13 | Agency Code | Auto Generated / Manual | Rezopia QA & BA
14 | Booking Number | Reset to Exec Travel Link teams preference | Rezopia QA & BA
15 | Invoice Number | Reset to Rezopia default | Rezopia QA & BA
16 | Quote Number | Reset to Exec Travel Link teams preference | Rezopia QA & BA
17 | Form of Payment | Verify Form of Payments | <Client>
18 | Product Types | Verify all the product types for correctness | <Client>
|  | Policies: if policies are not available at product level then define payment and cancellation polices at product type level | <Client>
|  | Also define Tax at product level if required | <Client>
19 | Products | All the products needs to be verified for correct inventory, pricing and Supplier information | <Client>
|  | Add payment and cancellation policies if required | <Client>
|  | Tax to be defined [if Any] | <Client>
|  | Inventory - Release all inventory and verify for data correctness | Rezopia QA & BA
20 | Partner Products | Check for LIVE partner URL, LIVE login credentials | <Client>
21 | Payment Gateway | Provide Live credentials for Payment Gateway applicable | <Client>
|  | Configure LIVE payment gateway URL, LIVE login credentials | Rezopia QA & BA
|  | Check for LIVE payment gateway URL, LIVE login credentials | Rezopia QA & BA
|  | Check the Address verification configuration (typically, the validation should be done on Zip Code) | <Client>
|  | In Payment console check whether Split payment is turned ON | <Client>
22 | SEO | Configure Google Analytics for B2C, B2B | <Client>
24-48 HRS Before GoLive
23 | Cleanup Process | Cancel & remove all the test bookings | Rezopia QA & BA
|  | Clean all the transactions before Golive & Empty transaction Log (audits) | Rezopia QA & BA
|  | Remove all test data from - Consumer, Branch, Agency, Agency Group, Supplier, All Product Types, Albums, Queues, Passenger Types, Form of Payment, Categories, Commission Sheet, Markup Sheet, Tax Definition, Bookings, Invoices, Custom Reports | Rezopia QA & BA
|  | Remove "rezopia from the address, it should be the actual email of Suppliers" Agency, Supplier and Product (hotel, activity etc) Email Address | Rezopia QA & BA
24 | Marketing site to Rezopia site | Verify if Marketing site of <<Client>> navigates to Rezopia booking site | <Client>
25 | Fare finder | Upon <<Client>> opting for Rezopia fare finder code, to ensure fare finder code is updated in Live site | Rezopia QA & BA
26 | Access Control | To ensure that all admin login password to be changed on the day of Going live | <Client>
|  | To ensure all pre-created users (testers/others) to be removed | Rezopia QA & BA

## 6.Go-Live
Go Live Steps
S.No | Tasks | Responsibility | Effort hours for Public Cloud client | Effort hours for Private Cloud client | Effort hours for Private Cloud client [LARGE] | Remarks
1 | Make sure Users are all setup in the admin. | REZEng | 8 | 12 | 16 | To make sure all users are able to access Call Center and Admin site
2 | Latest Operation Database to moved to Production Environment | RezInfra | 4 | 12 | 16 | Once clients certifies the Operation Environemnt then same database will be moved to Production Environemtn.When moving the database we need to makes sure Images,Products, Users, Configuration setups, Product type setup, Custom Attributes & Notifications to be moved to Production Environemnt
3 | Operations Readiness - Admin module/Call Center | RezEng | 8 | 12 | 16 | Rezopia team will be cleaning up all the old bookings and test products with the name Rezopia
4 | Third party components installation into the code (iZenda, Telerik, Expert PDF) | RezInfra | 4 | 8 | 8
5 | Domain mapping issue resolution (multi site. Single site ) | RezInfra | 4 | 4 | 12
6 | Production Infrastructure Verification | RezInfra | 4 | 4 | 8
7 | Copy the data and images from Ops Env to Prod Env | RezInfra | 8 | 8 | 12 | Rezopia team will be cleaning up all the old bookings and test products with the name Rezopia
8 | Public access for B2C - Security group change | RezInfra | 2 | 2 | 4
9 | DNS switch over strategy and Implementation | Client & Rezopia | 2 | 2 | 4
| Total |  | 44 | 64 | 96
Note: Based on the client size, these efforts might need to be updated/looked-at

## Public Cloud Pricing
Setup Fee (One Time)
| Starter | Professional | Premium | Enterprise
Base System (Negotiated Products + Packaging. Includes Consumer Site + Call Center) | 12000 | 12000 | 12000 | 12000
Partner Connectivity (existing connections) | N/A | $2500 per partner connectivity | $2500 per partner connectivity | $2500 per partner connectivity
Flights (GDS connectivity) | N/A | 4000 | 4000 | 4000
B2B | N/A | 2500 | 2500 | 2500
Web Services | N/A | N/A | $4000 per connection | $4000 per connection
External Accounting Interface (QuickBooks) | 2500 | 2500 | 2500 | 2500
Supplier Extranet System | N/A | 2500 | 2500 | 2500
Micro-Site | N/A | N/A | $2500 for each micro-site | $2500 for each micro-site
Miscellaneous Services
Data Loading | $18 per hour
Marketing Web site Creation | $5,000 - $20,000
Training (6 hours included) | $150 / hr
Subscription Fee (Monthly)
Option 1 (Product Unit based pricing)
| Starter | Professional | Premium | Enterprise
Base System (Negotiated Products + Packaging. Includes Consumer Site + Call Center) | 1000 | 2500 | 5000 | 10000
No of free product units | 250 | 1000 | 5000 | 15000
Cost per unit | 4 | 2.5 | 1 | 0.66667
Cost for each additional product unit | 6 | 3 | 1.5 | 0.5
Max # of users | 3 | 10 | 50 | 100
Max Storage | TBD | TBD | TBD | TBD
B2B | N/A | 250 | 250 | 250
Web Services (requires B2B) | N/A | N/A | $500 + $100 per connection | $500 + $100 per connection
Flights (GDS connectivity) | N/A | 400 | 400 | 400
External Accounting Interface | 50 | 150 | 150 | 150
Supplier Extranet System | N/A | 150 | 150 | 150
Micro-Site | N/A | N/A | 150 | 150
Option 2 (transaction based pricing)
| Starter | Professional | Premium | Enterprise
Minimal Monthly Spend | 1000 | 2500 | 5000 | 10000
Transaction Fee | 2.75% | 1.5% | 1% | 0.5%
For B2B add $250 to the minimal monthly spend. For GDS flights add $400 to the minimal monthly spend. For each micro-site add $150 to the minimal monthly spend.
25000

## Private Cloud Pricing
Private Cloud Setup Fees (one Time)
Core System (without 3rd party connections and Rezopia Web Service Interface) | 125000
Agency (B2B) distribution channel | 8000
Existing Flights GDS Connectivity (Sabre or Galileo) | 12000
Existing 3rd party Hotels, Cars, Activity or Channel manager connectivity | $4,000 per connection
Rezopia Web Service | $4,000 per connection
Each micro-site | 5000
Monthly Subscription Fees (Option 1)
Minimal Monthly Spend | Transaction Fee
5000 | 1.25%
10000 | 0.75%
15000 | 0.5%
For B2B distribution channel, add $10 per agency to the minimal monthly fee or $250 per month (depends on client)
For GDS flights add $500 per month to the minimal monthly fee.
For Rezopia web services add $250 per connection to the minimal monthly fee.
For each micro-site add $400 per month to minimal monthly fee
Monthly Subscription Fees (Option 2)
Minimal Monthly Fee | No of free product units per month | Cost for each additional product unit
10000 | 7500 | 2
15000 | 15000 | 1.25
25000 | 35000 | 0.75
A product unit corresponds to a flight ticket, a hotel room, an activity, a rental car etc. So for example if a reservation comprises of 1 hotel room, 2 transfers and 2 activities, then that corresponds to 5 product units in one reservation. If a pre-packaged tour is not broken down into individual components when loaded into Rezopia, then the number of product units = number of days in a pre-packaged tour.
For B2B distribution channel, add $10 per agency to the minimal monthly fee or $250 per month (depends on client)
For GDS flights add $500 per month to the minimal monthly fee.
For Rezopia web services add $250 per connection to the minimal monthly fee.
For each micro-site add $400 per month to minimal monthly fee